# Project brief: Education Center Management System

## How to use this document

This is a planning brief, not a finished spec. Read it fully, then produce an implementation plan before writing code: proposed architecture, data model, milestone breakdown, and a list of open questions/decisions that need a human answer before or during build. Flag any requirement below that is ambiguous or conflicts with another, rather than silently picking an interpretation.

A working front-end prototype already exists at education-management-system.jsx (in-memory React, no backend). Treat it as a reference for the intended UI flows and role permissions, not as the target architecture — it has no database, no auth, and no real WhatsApp integration.

## Goal

Build a multi-tenant-free (single center), role-based web application that lets an education center manage courses, teachers, students, parents, attendance, homework, feedback, and daily WhatsApp updates to parents.

## Roles and permissions

| Role | Created by | Can do |
| --- | --- | --- |
| Admin | Pre-provisioned (one main account) | Full read/write access to all data. Creates assistant accounts. |
| Assistant | Admin | Create/edit courses, create teacher accounts, create student (+auto-created parent) accounts, record teacher attendance, record student attendance (with timestamp), assign daily homework, write daily parent feedback, send WhatsApp summaries, manage course booking/payment status. |
| Teacher | Assistant | View own courses and enrolled students, view/edit own weekly calendar, add material links visible to enrolled students, mark own students' attendance. Cannot see other teachers' courses/students. |
| Student | Assistant (auto-created) | Read-only view of own enrolled courses, teacher(s), schedule, attendance history (with time), feedback, homework, material links, payment status. |
| Parent | Assistant (auto-created alongside student) | Same read-only scope as their child(ren)'s student view, plus the WhatsApp message history sent to them. Supports one parent linked to multiple children. |

Enforce role scoping at the API/data layer, not just hidden UI — a teacher's token must not be able to fetch another teacher's course or student data by guessing an ID.

## Auto-provisioned credentials

When the assistant creates a student, a parent account is created in the same action (unless one already exists for that phone number — support one parent with multiple children). When the assistant creates a teacher, only a teacher account is created.

- Username = the person's phone number (E.164 or local format — decide and validate consistently).

- Password = system-generated (define length/entropy; recommend forcing a password reset or at minimum surfacing a "must change password" flag on first login rather than emailing/texting the raw password anywhere insecure).

- The generated credentials must be shown once to the assistant/admin who created the account so they can share them with the family, and never displayed in plaintext again after that.

## Course catalog (fixed types — do not let types 1–6 below be freely edited, only which teacher/schedule/price/description attaches to an instance)

- 1 session/week — 4 sessions/month

- SAT Intermediate — 1 session/week — 5 sessions/month

- GPA Course — 2 sessions/week — 8 sessions/month

- SAT Basics — 2 sessions/week — 10 sessions/round

- EST Basics — 2 sessions/week — 10 sessions/round

- Advanced Course — 14 sessions/round

Each course instance the assistant creates needs: name, type (from the six above), assigned teacher, description, cover image, weekly schedule (day + time, count of slots implied by the type's sessions/week), price, whether trial-session booking is enabled, and it must appear on student/parent dashboards immediately once created.

Scheduling conflict rule: a teacher cannot be assigned two course schedule slots that fall on the same day and overlapping time. Validate this both on course creation and on any later edit to a course's schedule or teacher assignment. Return a clear conflict error naming the colliding course, day, and time rather than a generic failure.

## Attendance

Two independent attendance streams, both need date + time-of-check-in, not just present/absent:

- Teacher attendance per session (assistant records; consider allowing teacher self-check-in as a v2 option).

- Student attendance per session, per course (assistant and the course's teacher can both record it).

Attendance history must be queryable per student (for the student/parent dashboards) and per teacher/course (for the assistant/admin dashboards).

## Homework and feedback

- Daily homework is assigned per course (assistant), visible to every enrolled student on that date.

- Daily feedback is per student per course (assistant), visible to that student and their parent(s) only.

## WhatsApp daily updates

Every day, a message summarizing that day's attendance, homework, and feedback for a given student should be assembled and sent to that student's parent(s) via WhatsApp, from the center's number 01559306667.

- This requires the WhatsApp Business Platform (Cloud API) or a BSP (e.g. Twilio, 360dialog, Gupshup) — a personal WhatsApp number cannot send automated/templated messages at scale and Meta requires template pre-approval for outbound business-initiated conversations. Flag this as a setup dependency (Meta Business verification, template approval, per-message cost) rather than something the agent can silently work around.

- Support both an assistant-triggered "send now" action per student and a scheduled daily batch job.

- Log every sent message (recipient, phone, timestamp, content, delivery status from the provider's webhook) and surface that log on the parent's dashboard and to the admin/assistant.

- Handle delivery failures (invalid number, opted out, template rejected) visibly rather than silently.

## Payments and booking status

Per student-per-course enrollment, track: booking status (trial / booked / not booked) and payment status (paid / unpaid), editable by the assistant and admin. Visible read-only on the student/parent dashboard.

## Non-functional requirements to plan for

- Data model: propose normalized entities for users (with role + role-specific fields), courses, course schedule slots, enrollments (join table carrying paid/booked status), attendance records, homework, feedback, materials, whatsapp message log.

- Auth: phone-number + password login per role, session/token based; passwords hashed (never stored/logged in plaintext beyond the one-time reveal at creation).

- Authorization: server-side role and ownership checks on every endpoint (a teacher only ever queries their own course IDs; a parent only their linked child IDs).

- Audit trail: who changed what (e.g., who marked attendance, who edited a course) and when — needed for a center handling money and attendance disputes.

- Timezone: confirm which timezone all session times/dates are stored and displayed in.

- Scale: single center, expect low hundreds of students/teachers — this does not need to be architected for multi-tenancy unless told otherwise.

- Localization: confirm whether the UI needs Arabic/English bilingual support (the business itself is Egypt-based per the WhatsApp number's country code).

## Deliverable expected from the planning pass

- Proposed tech stack (backend framework, database, hosting, WhatsApp provider) with brief justification.

- Entity-relationship diagram or schema outline.

- API surface outline grouped by role.

- Milestone plan (e.g., auth + roles → courses + conflict detection → attendance/homework/feedback → WhatsApp integration → dashboards polish).

- A written list of open questions for the business owner (e.g., exact password policy, phone number format, what happens when a student is enrolled in multiple courses with different teachers who each want to message the parent, refund/cancellation handling for bookings, whether teachers can be assigned multiple subjects, whether admin can also act as an assistant).

Do not begin implementation until the plan and open-questions list have been reviewed.

# MCA Academy — Implementation Plan

Planning pass for the Education Center Management System, per `agent-planning-brief.md`.

Reference UI/permissions prototype: `education-management-system.jsx` (in-memory React, not the target architecture).

**Status: awaiting review. No implementation until the open questions in §8 are answered.**

Written to be handed to an implementing agent. §6 is the executable phase/sprint breakdown; §7 is the conventions that agent must follow.

Decisions already locked by the owner:

| Decision | Choice |

|---|---|

| UI | Flask + Jinja2 server-rendered, HTMX for interactivity |

| Language | Bilingual Arabic / English with a user toggle, RTL when Arabic |

| Database | SQLite in dev, Postgres-ready via SQLAlchemy; Postgres on deploy |

| WhatsApp | Full composer + log built now; actual send behind a pluggable provider, disabled until Meta approval |

---

## 1. Tech stack

| Layer | Choice | Why |

|---|---|---|

| Framework | Flask 3.x, app-factory + Blueprints | Asked for; blueprints keep the six role areas separable |

| ORM | SQLAlchemy 2.x + Flask-SQLAlchemy | Same models on SQLite and Postgres |

| Migrations | Alembic (Flask-Migrate) | Terms text and course types get versioned/seeded through migrations |

| Auth | Flask-Login, server-side cookie sessions | Server-rendered app — no reason to hand out JWTs |

| Passwords | Argon2id (`argon2-cffi` via passlib) | Current default; bcrypt acceptable fallback |

| Forms/CSRF | Flask-WTF | Every mutating form is CSRF-protected; this is not optional for cookie auth |

| i18n | Flask-Babel | `.po` catalogs for AR/EN, `dir="rtl"` driven by locale |

| Interactivity | HTMX + a little Alpine.js | Attendance marking, conflict checking, live search — no Node build step |

| CSS | Hand-written CSS with the prototype's brand tokens (navy `#16233F`, gold `#C99A3D`, cream `#F7F5F0`) + logical properties (`margin-inline-start` etc.) | Logical properties mean one stylesheet works LTR and RTL |

| Scheduled jobs | `flask send-daily-updates` CLI command driven by system cron | Survives app restarts and redeploys, unlike an in-process APScheduler |

| WhatsApp | `WhatsAppProvider` interface with `NullProvider` (log only) → `CloudApiProvider` later | Nothing in the build blocks on Meta verification |

| Hosting | Single small VPS (Hetzner/DigitalOcean) or Railway/Render + managed Postgres | Low hundreds of users; no need for anything elastic |

| Server | gunicorn behind nginx (or the PaaS router), TLS via Let's Encrypt | — |

Uploaded course cover images go to local disk (`instance/uploads/`) behind an authenticated route, with the path stored in the DB. If we move to a PaaS with an ephemeral filesystem, this becomes S3-compatible object storage — the storage call sits behind one small module so it's a one-file swap.

### Project layout

```

app/

__init__.py            # create_app(), extension init, blueprint registration

config.py              # Dev / Prod / Test configs

models/                # one module per aggregate

services/              # ALL business rules + authorization live here

auth.py  courses.py  scheduling.py  attendance.py

enrollments.py  whatsapp.py  terms.py  audit.py

blueprints/

auth/  admin/  assistant/  teacher/  portal/   # portal = student+parent

templates/             # base.html + per-blueprint folders + _partials/ for HTMX

static/

translations/          # ar/ and en/ LC_MESSAGES

cli.py                 # seed, create-admin, send-daily-updates, generate-sessions

migrations/

tests/

```

**Rule the codebase enforces:** route handlers never query models directly. They call a service function that takes `current_user` as its first argument and returns only rows that user is allowed to see. That is what makes §4 real instead of decorative.

---

## 2. Data model

### 2.1 The one significant departure from the brief

The brief describes attendance "per session" but its suggested entity list only has *course schedule slots*. A weekly slot ("Sunday 16:00") is a recurring pattern, not a thing you can attend. The prototype papers over this by keying attendance on `(course, date)`.

**I propose materializing a `sessions` table** — concrete dated session instances generated from a course's slots plus its start date and its type's total session count.

Without it, these requirements have nowhere to live:

- "session 7 of 10" progress toward a round

- teacher-cancelled sessions being *rescheduled* (a session whose date moves)

- the teacher-absence / student-absence payout rules in the teacher terms

- makeup sessions, which by definition don't sit on a weekly slot

- distinguishing "no session today" from "session today, nobody marked it"

It costs one generator function and one extra table. I recommend it; flagging it because it's a deliberate deviation from the brief's entity list.

Second, smaller departure: **teacher attendance lives on the `sessions` row** (`teacher_status`, `teacher_checked_in_at`), not in a parallel `attendance_records` table with `type='teacher'` as the prototype does. There is exactly one teacher per session, so a separate row is redundant and makes the "did this session actually run" query awkward.

### 2.2 Schema

```mermaid

erDiagram

users ||--o| teacher_profiles : "role=teacher"

users ||--o| student_profiles : "role=student"

users ||--o{ parent_links : parent

users ||--o{ parent_links : student

users ||--o{ terms_acceptances : accepts

terms_versions ||--o{ terms_acceptances : version

course_types ||--o{ courses : classifies

users ||--o{ courses : teaches

courses ||--o{ course_slots : "weekly pattern"

courses ||--o{ sessions : "dated instances"

course_slots ||--o{ sessions : generates

courses ||--o{ enrollments : has

users ||--o{ enrollments : student

courses ||--o{ materials : has

courses ||--o{ homework : has

sessions ||--o{ attendance_records : records

users ||--o{ attendance_records : student

sessions ||--o{ feedback : "optional link"

courses ||--o{ feedback : about

users ||--o{ feedback : student

users ||--o{ whatsapp_messages : "about student"

users ||--o{ audit_log : actor

```

**users** — `id, role(admin|assistant|teacher|student|parent), full_name, phone(unique, E.164), username(=phone, unique), password_hash, must_change_password(bool), locale(ar|en), is_active, created_by_id, created_at, updated_at`

**teacher_profiles** — `user_id(PK/FK), subject, payout_share(default 0.60), notes`

**student_profiles** — `user_id(PK/FK), school, grade, notes`

**parent_links** — `parent_id, student_id, relation` · unique(parent_id, student_id) — a true many-to-many, so one parent covers several children *and* a child can have two parents

**course_types** — `id(1..6), code, label_en, label_ar, sessions_per_week, cycle(month|round), total_sessions` — seeded by migration, **no CRUD route exists for this table**, which is how "types 1–6 are not freely editable" gets enforced.

**courses** — `id, name, course_type_id, teacher_id, description, cover_image_path, price_egp, trial_enabled, status(draft|active|archived), start_date, created_by_id, timestamps`

**course_slots** — `id, course_id, weekday(0=Sat..6=Fri), start_time(local wall clock), duration_minutes(default 90)`

→ `duration_minutes` is what makes "overlapping time" checkable; see §3.

**sessions** — `id, course_id, slot_id(nullable — null = makeup/ad-hoc), session_date, start_time, end_time, sequence_no, status(scheduled|held|cancelled_by_teacher|cancelled_by_center|rescheduled), rescheduled_to_id(nullable), teacher_id, teacher_status(present|absent|late|null), teacher_checked_in_at, recorded_by_id, notes`

**enrollments** — `id, course_id, student_id, booking_status(trial|booked|not_booked), payment_status(paid|unpaid), amount_due, enrolled_at, created_by_id` · unique(course_id, student_id)

**attendance_records** — `id, session_id, student_id, status(present|absent|late|excused), checked_in_at(timestamp), recorded_by_id, recorded_at` · unique(session_id, student_id)

**homework** — `id, course_id, session_id(nullable), for_date, text, created_by_id, created_at`

**feedback** — `id, course_id, student_id, session_id(nullable), for_date, text, created_by_id, created_at`

**materials** — `id, course_id, title, url, created_by_id, created_at`

**terms_versions** — `id, audience(teacher|student_parent), version(int), body_ar, body_en, effective_from, is_current` — seeded with v1 from the Arabic texts already in the prototype

**terms_acceptances** — `id, user_id, terms_version_id, accepted_at, ip, user_agent` · unique(user_id, terms_version_id)

→ The gate is "does an acceptance exist for the *current* version for my audience", not a boolean on the user. Bumping the text to v2 automatically re-prompts everyone, which is exactly what the brief asked for.

**whatsapp_messages** — `id, student_id, parent_id, to_phone, from_phone, template_name, body, status(queued|sent|delivered|read|failed), provider_message_id, error_code, error_detail, batch_date, created_by_id(null=cron), created_at, sent_at, delivered_at`

**audit_log** — `id, actor_id, action, entity_type, entity_id, before_json, after_json, ip, created_at`

### 2.3 Timezone

All session times are **Africa/Cairo**. Note Egypt reintroduced DST in 2023 (last Friday of April → last Thursday of October), so this is a live concern, not a formality.

- `session_date` + `start_time` are stored as **naive local wall-clock**. "Sunday 16:00" must stay 16:00 across a DST boundary — converting to UTC would silently shift half the year's sessions by an hour.

- All *event* timestamps (`checked_in_at`, `accepted_at`, `sent_at`, audit rows) are stored **timezone-aware UTC** and rendered in Cairo time.

### 2.4 Passwords & phone numbers

- **Phone:** input accepted as local (`01xxxxxxxxx`) or international, normalized to E.164 (`+201xxxxxxxxx`) on save via `phonenumbers`. Login normalizes before lookup, so either form works at the login box. Unique index on the normalized value.

- **Generated password:** 10 characters from a 32-char alphabet with ambiguous glyphs removed (no `0 O 1 l I`), via `secrets.choice` — ~50 bits. Hashed immediately; the plaintext exists only in the response that renders the creation confirmation and is never written to the DB, the logs, or a flash cookie.

- `must_change_password=True` on every generated account. Login order is: **authenticate → forced password change → terms acceptance → dashboard.** No route reachable until both gates clear (enforced in a `before_request` hook, not in templates).

- Because the plaintext is genuinely unrecoverable, **assistants and admins get a "regenerate password" action** on any account they created. The brief doesn't mention this and the system is unusable without it — an assistant who closes the tab before writing the password down has otherwise locked the family out permanently.

---

## 3. Scheduling conflict rule

The brief says a teacher can't hold two slots on the same day at **overlapping** times. The prototype only compares exact-equal start strings, so a 16:00 and a 16:30 class collide in reality but pass its check.

Implementation:

- Every slot carries `duration_minutes`, so a slot is a real interval `[start, start + duration)`.

- Overlap test: `a.start < b.end AND b.start < a.end` on the same weekday.

- Checked in `services/scheduling.py::assert_no_conflicts(teacher_id, slots, exclude_course_id)`, called on **course create, course edit, teacher reassignment, and slot edit** — all four paths, since the brief calls out edits specifically.

- The error names the colliding course, day, and time: *"Mr. Ahmed Fathy is already teaching «Math — GPA Booster» on Sunday 16:00–17:30, which overlaps 16:30–18:00."*

- The same check runs live over HTMX as the assistant edits the slot form, before submit.

Two things to decide (§8): whether **students** should also be conflict-checked across their enrolled courses, and whether **rooms** are a constraint. Neither is in the brief; both are cheap to add now and awkward to retrofit.

---

## 4. Authorization model

Enforced in services, not templates. Every scoped read goes through a helper that filters by ownership and raises 404 (not 403 — a 403 confirms the ID exists) when the row is out of scope.

| | Admin | Assistant | Teacher | Student | Parent |

|---|---|---|---|---|---|

| Assistants CRUD | ✅ | — | — | — | — |

| Courses CRUD | ✅ | ✅ | read own | read enrolled | read child's |

| Teacher/student/parent accounts | ✅ | ✅ | — | — | — |

| Student attendance | ✅ | ✅ | own courses | read own | read child's |

| Teacher attendance | ✅ | ✅ | (v2: self check-in) | — | — |

| Homework | ✅ | ✅ | read own courses | read enrolled | read child's |

| Feedback | ✅ | ✅ | read own courses | read own | read child's |

| Materials | ✅ | ✅ | CRUD own courses | read enrolled | read child's |

| Booking / payment status | ✅ | ✅ | — | read own | read child's |

| WhatsApp send + log | ✅ | ✅ | — | — | read own messages |

| Audit log | ✅ | — | — | — | — |

Scoping helpers: `courses_for(user)`, `students_for(user)`, `sessions_for(user)`, `get_course_or_404(user, id)`. A teacher's session simply cannot produce another teacher's course object — there is no code path that returns one.

**Assumption flagged:** admin is treated as a strict superset of assistant (the brief says "full read/write access to all data" but its own open-questions list asks whether admin can act as an assistant). Easy to narrow later; hard to widen.

---

## 5. Route surface

Bilingual routes stay in one URL space; locale is a user preference plus a `?lang=` override, not a URL prefix.

**Auth** — `GET/POST /login`, `POST /logout`, `GET/POST /password/change` (forced), `GET/POST /terms` (gate), `GET/POST /me/language`

**Admin** — `/admin/` overview · `/admin/assistants` list/create · `POST /admin/users/<id>/regenerate-password` · `POST /admin/users/<id>/deactivate` · `/admin/audit` · `/admin/terms` (list versions, publish new version)

**Assistant** (admin has all of these too)

- Courses: `/courses`, `/courses/new`, `/courses/<id>`, `/courses/<id>/edit`, `POST /courses/<id>/slots`, `POST /courses/check-conflicts` (HTMX), `POST /courses/<id>/generate-sessions`

- People: `/people/teachers`, `/people/students` (create student → auto-creates or links parent), `/people/<id>`

- Enrollment: `POST /courses/<id>/enroll`, `PATCH /enrollments/<id>` (booking + payment status)

- Attendance: `/attendance`, `/sessions/<id>/attendance` (mark students + teacher, HTMX per row), `/attendance/log` (filter by teacher/course/date)

- Homework & feedback: `/courses/<id>/homework`, `/courses/<id>/feedback`

- WhatsApp: `/whatsapp` (per-student preview + send now), `POST /whatsapp/send/<student_id>`, `POST /whatsapp/send-batch`, `/whatsapp/log`

**Teacher** — `/teacher/` · `/teacher/courses` · `/teacher/courses/<id>` · `/teacher/calendar` (weekly) · `/teacher/materials` CRUD · `/teacher/sessions/<id>/attendance`

**Portal** (student and parent share templates; parent gets a child switcher + WhatsApp history)

`/portal/` · `/portal/courses/<id>` · `/portal/attendance` · `/portal/homework` · `/portal/feedback` · `/portal/messages` (parent only) · `POST /portal/child/<id>/select` (parent only)

**Webhooks** — `POST /webhooks/whatsapp` (signature-verified delivery status; inert until the provider is live)

---

## 6. Execution plan — phases and sprints

Twelve phases, P0 through P11, each broken into sprints. Every sprint states what to build, which files it owns, and the condition that proves it's finished. Phases run in order; sprints inside a phase may run in parallel unless a dependency is noted.

Rough total: **4–5 weeks** of focused work. WhatsApp go-live is gated on Meta approval, not on us.

**Phase map**

| Phase | Name | Est. | Gate to leave it |

|---|---|---|---|

| P0 | Foundation & tooling | 1–2 d | Bilingual empty shell runs, `pytest` green |

| P1 | Identity, auth, onboarding gates | 3–4 d | Role isolation proven by test |

| P2 | Catalog: courses, slots, conflicts | 3–4 d | Overlap rejected with a named-course error |

| P3 | Sessions & attendance | 4–5 d | Timestamped attendance, teacher scoped to own sessions |

| P4 | Homework, feedback, materials | 2 d | Feedback visible to exactly one family |

| P5 | Enrollment, booking, payment | 1–2 d | Statuses editable by staff, read-only on portal |

| P6 | WhatsApp | 3–4 d | Batch runs, log complete, failures visible |

| P7 | Dashboards & portal polish | 3–4 d | Every role has a real landing page in both languages |

| P8 | Audit trail & oversight | 2 d | Every mutating route provably writes an audit row |

| P9 | Security hardening | 2–3 d | Full role × route authorization matrix passes |

| P10 | Deploy & UAT | 2 d | Staff walkthrough on production data |

| P11 | Final acceptance audit | 1–2 d | Every brief requirement traced to code + test |

---

### P0 — Foundation & tooling

No user-visible features. Everything after this depends on P0 being solid, so don't rush it.

**S0.1 — Repo, tooling, config**

- Build: `pyproject.toml` (or `requirements.txt` + `requirements-dev.txt`), `.gitignore` covering `.venv*/ instance/ *.db __pycache__ .env`, ruff + black config, `.env.example`, `Config`/`DevConfig`/`TestConfig`/`ProdConfig` classes reading from env, `create_app()` factory, `GET /healthz`.

- Files: `app/__init__.py`, `app/config.py`, `wsgi.py`, `.env.example`

- Done when: `flask run` serves `/healthz` → `{"status":"ok"}`; no secret has a hardcoded default outside `DevConfig`.

**S0.2 — Data layer bootstrap**

- Build: Flask-SQLAlchemy + Flask-Migrate init, declarative base with `id` / `created_at` / `updated_at` mixins, Python enums for every status column in §2.2, first (empty) Alembic revision.

- Files: `app/extensions.py`, `app/models/base.py`, `app/models/enums.py`, `migrations/`

- Done when: `flask db upgrade` runs clean on a fresh SQLite file and on a Postgres URL.

**S0.3 — Layout & design system**

- Build: `base.html` with the prototype's brand tokens as CSS custom properties, sidebar + topbar shell, flash-message region, HTMX + Alpine included locally (no CDN), reusable partials for card / pill / button / form-field matching the prototype's look.

- Files: `app/templates/base.html`, `app/templates/_partials/*`, `app/static/css/app.css`

- Done when: the shell renders identically in LTR and RTL because layout uses logical properties (`margin-inline-start`, `padding-inline`, `text-align: start`) — **no bare `left`/`right` anywhere in the stylesheet.**

**S0.4 — Bilingual i18n**

- Build: Flask-Babel, `babel.cfg`, `ar`/`en` catalogs, locale selector (user preference → `?lang=` override → `Accept-Language` → default), `<html lang dir>` driven by locale, language toggle in the topbar, `POST /me/language`.

- Files: `app/i18n.py`, `app/translations/`, `babel.cfg`

- Done when: toggling to Arabic flips the whole shell to RTL and persists across requests for a logged-out visitor (session) and a logged-in user (DB).

**S0.5 — Test harness**

- Build: pytest fixtures — `app`, `client`, `db_session` (transaction rollback per test), and a `users` factory that mints one user of each of the five roles plus a logged-in client per role.

- Files: `tests/conftest.py`, `tests/factories.py`, `tests/test_smoke.py`

- Done when: `pytest` is green and a test can do `as_teacher.get("/admin/")` in one line. **Every later sprint's "done when" is written as a test using these fixtures.**

**S0.6 — Audit + storage primitives**

- Build: `audit_log` table, `services/audit.py::record(actor, action, entity, before, after)` with JSON diffing, and a storage module wrapping file writes (local disk now, object storage later behind the same two functions).

- Files: `app/models/audit.py`, `app/services/audit.py`, `app/services/storage.py`

- Done when: `record()` writes a row with a usable before/after diff. Built now — not in P8 — so every sprint can instrument as it goes rather than retrofitting.

---

### P1 — Identity, auth, onboarding gates

**S1.1 — User model & credentials service**

- Build: `users` + the three profile tables + `parent_links` per §2.2. Phone normalization to E.164 via `phonenumbers` (accepts `01xxxxxxxxx`). Argon2id hashing. Password generator per §2.4 (10 chars, ambiguous glyphs stripped, `secrets`).

- Files: `app/models/user.py`, `app/services/auth.py`

- Done when: `01011112222` and `+201011112222` resolve to the same user; a generated password never appears in the DB, in `repr()`, or in any log line.

**S1.2 — Login / logout**

- Build: Flask-Login wiring, login form (phone + password) styled per the prototype, secure session cookies (`HttpOnly`, `SameSite=Lax`, `Secure` in prod), generic failure message that doesn't reveal whether the phone exists, basic per-IP rate limit.

- Done when: wrong password and unknown phone produce byte-identical responses.

**S1.3 — Forced password change gate**

- Build: `before_request` hook redirecting any user with `must_change_password=True` to `/password/change`, with only that route and logout reachable.

- Done when: a test proves a freshly created user hitting *any* other URL lands on the change form.

- Depends on: S1.1.

**S1.4 — Terms versioning model & seed**

- Build: `terms_versions` + `terms_acceptances`, seed migration inserting v1 for both audiences with the Arabic texts from `education-management-system.jsx` (lines 16–57), `services/terms.py::current_version_for(user)` and `needs_acceptance(user)`.

- Done when: acceptance is resolved by *querying for an acceptance row matching the current version* — never by a boolean on the user — so publishing v2 re-prompts everyone automatically.

- **Blocked on open question 6** (English terms text). Build the AR side; leave `body_en` nullable and fall back to Arabic until answered.

**S1.5 — Terms gate screen**

- Build: full-page (not dismissible-modal) terms screen, RTL, full scrollable text, required checkbox before the continue button enables, logout the only alternative exit. `before_request` hook ordered *after* the password gate.

- Done when: a teacher/student/parent who hasn't accepted cannot reach any dashboard URL by typing it directly; admin and assistant are never shown the screen.

- Depends on: S1.3, S1.4.

**S1.6 — Account creation & credential reveal**

- Build: admin → assistant. Assistant → teacher. Assistant → student, which in the same transaction links an existing parent by phone or creates a new one. One-time credential reveal rendered in the POST response only. "Regenerate password" action per §2.4.

- Done when: creating a student whose parent phone already belongs to a parent *links* rather than duplicating; the same phone belonging to a teacher is refused with a clear message; the plaintext password appears in exactly one HTTP response and nowhere else.

- **Blocked on open question 1** (shared student/parent phone). Implement recommendation (b) — parent-only account when one phone is supplied — behind a config flag so the other options are a small change.

**S1.7 — Authorization primitives**

- Build: `@require_role(...)` decorator, the scoping helpers named in §4 (`courses_for`, `students_for`, `sessions_for`, `get_course_or_404`), and the 404-not-403 policy.

- Files: `app/services/scoping.py`, `app/decorators.py`

- Done when: a test asserts every role's access to a representative route of every other role's blueprint. This test file grows in every later phase and becomes the P9 matrix.

---

### P2 — Catalog: courses, slots, conflicts

**S2.1 — Course types seed**

- Build: `course_types` seeded by migration with the six types from the brief. **No create/edit/delete route exists for this table** — that absence is how "types 1–6 are not freely editable" is enforced.

- **Blocked on open questions 2 and 3** (type 6 sessions/week; type-vs-name semantics). Seed `sessions_per_week = 2` for type 6 as the prototype assumes, in a single migration that's trivial to amend.

**S2.2 — Course CRUD**

- Build: create/edit/archive, cover image upload through `services/storage.py` with type + size validation, served via an authenticated route (never a raw static path).

- Done when: a course created by an assistant appears immediately on the enrolled students' and parents' dashboards, per the brief.

**S2.3 — Slot editor**

- Build: slot rows sized by the selected type's `sessions_per_week` — picking a 2/week type renders exactly two day+time rows. `duration_minutes` per slot.

- **Blocked on open question 4** (default duration). Use 90 minutes.

**S2.4 — Conflict detection service**

- Build: `services/scheduling.py::assert_no_conflicts(teacher_id, slots, exclude_course_id)` using the half-open interval test from §3. Wired into **all four** mutation paths: course create, course edit, teacher reassignment, slot edit.

- Done when: a test proves 16:00–17:30 and 16:30–18:00 on the same weekday collide (the prototype's exact-match check passes this pair, which is the bug being fixed), and the error message names the colliding course, day, and time range.

**S2.5 — Live conflict preview**

- Build: HTMX `POST /courses/check-conflicts` re-rendering a warning partial as the assistant edits the slot form.

- Done when: the warning appears before submit and the server still re-validates on submit — the live check is a convenience, never the enforcement point.

**S2.6 — Scoped course views**

- Build: course list/detail for assistant (all), teacher (own only), student (enrolled only), parent (children's only), all through S1.7 helpers.

- Done when: a teacher requesting another teacher's course ID gets 404.

---

### P3 — Sessions & attendance

**S3.1 — Session generation**

- Build: `services/scheduling.py::generate_sessions(course)` materializing dated sessions from slots + start date + the type's `total_sessions`, numbered `sequence_no` 1..n. Idempotent — re-running never duplicates. Exposed as a course action and a `flask generate-sessions` CLI command.

- **Blocked on open question 5** (round start dates). Implement assistant-set `start_date` per course.

- Done when: a 2/week 10-session course produces exactly 10 rows on the right weekdays, and running it twice still produces 10.

**S3.2 — Session lifecycle**

- Build: cancel (by teacher vs by center — the distinction drives the payout rules in the teacher terms), reschedule to a new date via `rescheduled_to_id`, and ad-hoc makeup sessions with `slot_id = NULL`.

- Done when: a cancelled session is excluded from attendance-required views but still visible in history with its reason.

**S3.3 — Student attendance**

- Build: marking UI per session (present/absent/late/excused) writing `checked_in_at`, one HTMX row per student. Both the assistant and the course's own teacher can record. Unique constraint on `(session_id, student_id)`; re-marking updates and audits rather than inserting.

- Done when: a teacher marking a session of a course they don't teach gets 404, and the recorded time is a real timestamp rather than the prototype's `HH:MM` string.

**S3.4 — Teacher attendance**

- Build: `teacher_status` + `teacher_checked_in_at` on the session, recorded by assistant/admin.

- Note: **open question 12** — teacher self check-in is v2, not built here.

**S3.5 — Attendance history & filters**

- Build: per-student history (portal), per-teacher and per-course history with date-range and teacher filters (staff), as the brief requires both query directions.

- Done when: a parent's history view returns only their linked children's rows, proven by a test that requests another child's ID.

---

### P4 — Homework, feedback, materials

**S4.1 — Homework** — per course per date, assistant-authored, visible to every enrolled student on that date. Optional `session_id` link.

**S4.2 — Feedback** — per student per course per date, assistant-authored. *Done when: a test proves student B cannot read student A's feedback and parent B cannot either — this is the tightest visibility scope in the system.*

**S4.3 — Materials** — teacher CRUD on their own courses, link + title, visible to enrolled students and their parents. URL validated and rendered with `rel="noopener noreferrer"`.

---

### P5 — Enrollment, booking, payment

**S5.1 — Enrollment** — enroll/unenroll a student into a course, unique per `(course, student)`.

**S5.2 — Statuses** — booking (trial / booked / not booked) and payment (paid / unpaid), editable by assistant and admin, every change audited.

**S5.3 — Trial handling** — `trial_enabled` on the course drives whether "trial" is an offerable booking status. **Blocked on open question 8** — assistant-only for now; no public booking page until answered.

**S5.4 — Portal display** — both statuses read-only on the student and parent dashboards. *Done when: no POST route in the portal blueprint can touch an enrollment.*

---

### P6 — WhatsApp

**External dependency — start this now, not at P6.** Meta Business verification for **01559306667**, a WhatsApp Business Account, and template pre-approval. Meta requires a pre-approved template for business-initiated messages; approval takes days to weeks and each conversation is billed. A personal number cannot do this. No amount of code shortens that lead time.

**S6.1 — Daily summary builder**

- Build: `services/whatsapp.py::build_daily_summary(student, date)` assembling that day's attendance, homework, and feedback, in the parent's locale.

- **Blocked on open question 7.** Implement one combined message per student per day (cheaper — Meta bills per conversation).

- Done when: unit-tested against a student with two courses, a student with no session that day, and a student with attendance but no feedback.

**S6.2 — Provider interface & message log**

- Build: `whatsapp_messages` table per §2.2. `WhatsAppProvider` ABC with `send(to, template, params) -> ProviderResult`. `NullProvider` logging a `queued`/`sent` row without calling out. Provider chosen by config.

- Done when: swapping providers is one env var and touches no calling code.

**S6.3 — Send-now UI + log**

- Build: assistant WhatsApp center — per-student preview of the assembled message, send button, and the full log (recipient, phone, timestamp, body, status).

**S6.4 — Scheduled batch**

- Build: `flask send-daily-updates` iterating active students, plus a cron entry. Idempotent on `(student_id, batch_date)` so a double-run or a retry can't double-send.

- Done when: running the command twice in one day sends once.

**S6.5 — Cloud API provider & webhook**

- Build: `CloudApiProvider` (written, disabled by config), `POST /webhooks/whatsapp` with signature verification updating delivery status, and **visible** failure surfacing — invalid number, opted out, template rejected — on the assistant dashboard, per the brief's explicit requirement that failures not be silent.

- Done when: a simulated failed webhook payload flips the row to `failed` and raises a dashboard warning.

**S6.6 — Parent message history** — the parent sees the log of messages sent to them, and only to them.

---

### P7 — Dashboards & portal polish

**S7.1 — Role landing dashboards** — admin (center-wide counters, unpaid enrollments, today's sessions), assistant (today's attendance to record, unsent summaries), teacher (today's sessions, my students), portal (next session, latest feedback, homework due).

**S7.2 — Teacher weekly calendar** — the seven-day grid from the prototype, editable per the brief's "view/edit own weekly calendar" (edit = request a change routed through the assistant, per the teacher terms — teachers must not silently rewrite their own schedule).

**S7.3 — Admin overview** — the counters and payment summary from the prototype's `AdminOverview`.

**S7.4 — Arabic catalogue completion** — every user-facing string extracted and translated; **needs a native Arabic reader to review before P10**, not machine translation.

**S7.5 — Responsive pass** — staff use desktop, but parents will open this on a phone. Portal templates must work at 375px.

---

### P8 — Audit trail & oversight

The audit service exists from S0.6 and sprints instrument as they go; this phase makes it complete and verifiable.

**S8.1 — Coverage sweep** — walk every mutating service function and confirm it calls `audit.record()` with a meaningful before/after. Expected coverage: account create/deactivate/password-regenerate, course create/edit/archive, slot and teacher-assignment changes, session cancel/reschedule, attendance mark and re-mark, homework/feedback/material create/edit/delete, enrollment and status changes, terms publication, WhatsApp send.

**S8.2 — Admin audit viewer** — `/admin/audit` filtered by actor, entity type, entity ID, and date range, with the before/after diff rendered readably. Read-only: no route may edit or delete an audit row.

**S8.3 — Coverage test** — a test that enumerates the app's POST/PATCH/DELETE routes and asserts each one produces an audit row, failing on any new uninstrumented route. This is what stops audit coverage from rotting after handoff.

**S8.4 — Retention** — **blocked on open question 13**; default to indefinite retention with an archival CLI stub.

*Phase gate: attendance and money changes are attributable to a named actor with a timestamp — the reason the brief asked for this at all.*

---

### P9 — Security hardening

**S9.1 — Transport & headers** — HTTPS enforced, HSTS, `X-Content-Type-Options`, `X-Frame-Options`, a CSP that permits the local HTMX/Alpine bundles and nothing remote, secure cookie flags verified in prod config.

**S9.2 — Authorization matrix** — the S1.7 test grown to full coverage: every role × every route, asserting allow or 404. This is the single most important test file in the repo; the brief's warning about guessing IDs is exactly what it defends.

**S9.3 — Input & injection review** — CSRF on every mutating form, autoescaping on (audit every `|safe`), file-upload type/size limits, all ORM queries parameterized, redirect targets validated against an allowlist.

**S9.4 — Secrets & logging review** — grep the codebase and a sample log for plaintext passwords, tokens, and full phone numbers; confirm the one-time reveal is the only place plaintext exists.

**S9.5 — Backup & restore drill** — nightly `pg_dump` to off-box storage, plus an actual restore into a scratch database. A backup that has never been restored is not a backup.

---

### P10 — Deploy & UAT

**S10.1 — Provision** — Postgres, app host, TLS, environment variables, object/file storage decision confirmed.

**S10.2 — Release** — gunicorn + nginx (or PaaS equivalent), `flask db upgrade` on deploy, health check, log aggregation, a written rollback procedure.

**S10.3 — Go-live data** — real admin account created interactively (never seeded with a known password), course types seeded, terms v1 published, demo data explicitly *not* loaded.

**S10.4 — Staff UAT** — walkthrough with the admin and an assistant covering: create a course, create a family, mark attendance, write feedback, send a summary. Fix what they hit.

---

### P11 — Final acceptance audit

The closing verification pass — distinct from P8's audit *trail* feature.

**S11.1 — Requirement traceability** — a table mapping every requirement in `agent-planning-brief.md` to the code that implements it and the test that proves it. Anything unmapped is either a gap or a consciously deferred item, and must be named as one.

**S11.2 — Role-scope re-verification** — re-run the P9 matrix against production configuration, since deploy-time config changes are where authorization regressions hide.

**S11.3 — Data integrity audit** — orphan check (enrollments without courses, sessions without slots that aren't makeups, parent links to deleted students), constraint verification, timezone spot-check across a DST boundary.

**S11.4 — Handover** — README with local setup, runbook for deploy/rollback/backup-restore, a document listing every open question and the answer it was built against, and the deferred-work list (teacher self check-in, payout reports, public trial booking, whatever else P0–P10 pushed).

---

## 7. Notes for the implementing agent

Read this before starting P0.

**Ground rules**

1. **Never query a model directly in a route handler.** Call a service function that takes `current_user` first and returns only permitted rows. This is the single convention that makes §4 real rather than decorative.

2. **404, not 403,** for out-of-scope resources — a 403 confirms the ID exists.

3. **Every mutating service call writes an audit row** (S0.6). Not optional, not deferred to P8.

4. **No plaintext password ever leaves the creation response.** Not in the DB, not in logs, not in a flash cookie, not in an email or SMS.

5. **No bare `left`/`right` in CSS.** Logical properties only, or the Arabic layout breaks.

6. **No CDN assets.** HTMX, Alpine, and fonts are vendored — the center may run on flaky connectivity, and a CSP that allows remote scripts is a needless hole.

7. **Session times are naive local wall-clock; event timestamps are aware UTC** (§2.3). Mixing these up silently shifts half the year's sessions.

**Definition of done for every sprint**

- Feature works for every role that should have it, and returns 404 for every role that shouldn't.

- Tests written using the S0.5 fixtures, covering the happy path plus the authorization negative case.

- User-facing strings wrapped in `_()` and present in both catalogs.

- Mutations audited.

- Alembic migration generated and tested both up and down.

- `ruff` and `pytest` clean.

**When you hit a blocked open question**

Seven sprints are marked blocked on §8. Do not stall the phase and do not silently invent an answer. Implement the recommendation named in the sprint, isolate it behind a config flag or a single migration, add a `# OPEN QUESTION n:` comment at the decision point, and list it in the handover doc. If a question is answered mid-build, the answer should touch one file.

**Do not**

- Do not build multi-tenancy. Single center, explicitly.

- Do not add a public-facing signup, booking, or marketing page — every account is staff-created (until question 8 says otherwise).

- Do not build payout calculation screens (question 9), teacher self check-in (question 12), or refund workflows (question 10) without an answer first.

- Do not introduce a Node build step. The UI decision was server-rendered Jinja specifically to avoid one.

- Do not treat `education-management-system.jsx` as the architecture. It is a UI and permissions reference with no auth, no persistence, and a conflict check that's demonstrably wrong (§3).

---

## 8. Open questions — need your answer

Ordered by how much they block. **1–6 block implementation.**

1. **Student and parent sharing one phone number.** Username = phone, and phone must be unique — but the prototype defaults the parent's phone to the student's, and many school-age students have no phone at all. Three ways out: (a) require distinct phones and refuse otherwise, (b) when there's one phone, create only the parent account and let the parent view the child (no student login), (c) drop phone-as-username and use a generated code. **My recommendation: (b).** Which do you want?

2. **Course type 6, "Advanced Course — 14 sessions/round", has no sessions-per-week.** The prototype guesses 2/week. Is it 2/week over 7 weeks, or something else?

3. **What is a course's `name` for, given the type already names the subject?** Types 2, 4, 5 and 6 embed a subject ("SAT Intermediate", "SAT Basics", "EST Basics", "Advanced"), but type 1 and 3 are generic, *and* every course instance also carries a free-text name. So "SAT Basics" could be both the type and the name. Should the type just define the *session pattern* (n/week, m/round) with subject living on the course, or should the type label be shown to students as-is?

4. **Session duration.** Real overlap detection needs a length. Is 90 minutes right as the default, and should it vary per course?

5. **Round start dates.** Session generation needs to know when a round begins. Does the assistant set a start date per course, or do sessions get created rolling week-by-week?

6. **English terms & conditions text.** You've chosen a bilingual UI, and I have both Arabic texts from the prototype. Do you want English translations of the terms (I can draft them for your review), or should the terms display in Arabic for everyone regardless of UI language? Legally this is your call, not mine.

7. **Multiple courses, one daily WhatsApp message.** A student in two courses with two teachers — one combined daily message per student (my recommendation, and cheaper: Meta bills per conversation), or one message per course?

8. **Who books a trial?** `trial_enabled` and a "trial" booking status exist, but there's no public-facing page in the brief. Is trial booking an assistant-only action, or do you want a public course page where a parent can request one?

9. **Teacher payouts.** The teacher terms specify a 60/40 split, end-of-round settlement, and specific rules for teacher-absence vs student-absence. That's a finance feature nobody listed in the requirements. Is a payout report in scope, or v2? (The session data model above supports it either way — I just won't build the screens.)

10. **Refunds and cancellations.** Payment status is only paid/unpaid. What happens when a booking is cancelled after payment, or a student withdraws mid-round?

11. **Can a teacher teach multiple subjects?** `teacher_profiles.subject` is currently singular, as in the prototype.

12. **Teacher self check-in** — brief lists it as a possible v2. Confirm it's out of scope for now.

13. **Data retention / backups.** How long do attendance and WhatsApp logs need to be kept, and where should nightly backups go?

---

## 9. Conflicts and gaps found in the brief

Raising these rather than picking silently, as instructed.

- **"Password shown once, never displayed again" has no recovery path.** An assistant who closes the tab locks the family out. Plan adds a regenerate action (§2.4).

- **Attendance "per session" with no session entity.** Resolved by materializing `sessions` (§2.1) — a deliberate departure from the brief's entity list.

- **"Overlapping time" is uncheckable without a duration field**, which the brief's data model doesn't include. Added (§3).

- **Course types conflate subject and schedule pattern** (question 3).

- **Types 4 and 5 are structurally identical** — 2/week, 10/round, differing only in name. Fine if types carry subject identity, redundant if they don't. Same root cause as question 3.

- **Parent auto-creation keyed on phone number** collides with question 1 and with the case where the phone already belongs to a teacher. Plan: check the phone across *all* roles, and if it belongs to an existing parent, link the new child; if it belongs to a non-parent, refuse with a clear message.

- **Teacher terms constrain business process, not software.** The exclusivity, 24-hour-notice, and emergency-phone-call rules are contractual and unenforceable in code. The app stores acceptance; it does not police them. Confirming that's understood.

- **The brief's "assistant records teacher attendance"** vs the teacher terms' payout consequences for teacher absence — recording is built, the payout arithmetic is question 9.